## Sheet1
Guidance on Introduction of Software Bill of Materials (SBOM) for Software Management Appendix: Checklist of actions for the introduction of SBOM (Provisional Translation)
This checklist is a list of items to be introduced in each of the following phases toward the introduction of SBOM: the environment and system development phase, the SBOM production and sharing phase, and the SBOM use and management phase. Items may be added or deleted, or the contents may be modified according to the reader's situation.
Phase | Step | Actions for the introduction of SBOM | Check
Environment and system development phase | Clarification the scope of the SBOM application | Clarify information about the target software, such as information about development language, component type, development tools, etc. | □
|  | Create an accurate configuration diagram of the target software and visualize the target of the SBOM application. | □
|  | Clarify the contractual form and business practices with users and suppliers of the subject software. | □
|  | Confirm regulations and requirements for SBOM regarding the target software. | □
|  | Clarify the constraints within the organization (e.g., system constraints, cost constraints) regarding the introduction of SBOM. | □
|  | Clarify the scope of the SBOM application 5W1H (Five Ws and How) based on the organized information. | □
| SBOM tools selection | Organize the viewpoints for the selection of SBOM tools considering the development language of the target software and the constraints within the organization. (Examples of selection perspectives: functions, performance, analyzable information, analyzable data format, cost, supported formats, component analysis method, support systems, coordination with other tools, form of provision, user interface, operation method, supported software languages, Japanese support, etc.) | □
|  | Evaluate and select multiple SBOM tools based on the organized viewpoints. | □
| SBOM tools installation | Check the requirements of the environment where the SBOM tool can be installed and set up the environment. | □
|  | Check the instruction manual and README file of the tool and then implement and configure an SBOM tool. | □
| Learning about SBOM tools | Learn how to use SBOM tools by checking the instruction manual and README file of the tool. | □
|  | Record know-how on how to use the tool and the outline of each function and share them within the organization. | □
SBOM production and sharing phase | Component analysis | Scan the target software and analyze the component information using an SBOM tool. | □
|  | Examine the analysis log of the SBOM tool and check whether the analysis has been correctly executed without any false positives or false negatives caused by errors or lack of information. | □
|  | Check the component analysis results to see if there are any false positives and false negatives. | □
| SBOM production | Determine the requirements for the SBOM to be produced, such as items, format, and output file format. | □
|  | Produce an SBOM that satisfies the requirements, by using the SBOM tool. | □
| SBOM sharing | Share an SBOM with the users and/or suppliers of the target software as necessary after determining the method of sharing the SBOM. | □
|  | Consider using electronic signature technology or other technologies to prevent falsification of the sharing of SBOM data. | □
SBOM use and management phase | Vulnerability management, license management, etc. | Based on the output of the SBOM tool, assess the severity, evaluate the impact, fix the vulnerabilities, check the residual risk, and provide information to the relevant organizations. | □
|  | Based on the output of the SBOM tool, check whether there is any violation of the OSS license. | □
| SBOM information management | Keep the created SBOM for a certain period of time, including the change history, so that it can be referred to in case of inquiries from outside the company, etc. | □
|  | Manage the information contained in the SBOM and the SBOM itself appropriately. | □